Project Proposal

Custom MCP Server — Claude M365 Per-User Access Control

Prepared for: [Client Name]     |     Date: [Date]     |     Version: 1.0

# Executive Summary

This proposal outlines the design and delivery of a custom MCP (Model Context Protocol) server to enable granular, centrally-enforced per-user access control between Claude and Microsoft 365. The engagement addresses a limitation of the built-in Claude M365 connector, which applies Graph API permission scopes tenant-wide and does not support per-user or per-group scope differentiation.

The solution will allow all users to access SharePoint through Claude while restricting Outlook access to a single designated user — enforced at the server level, with no dependency on individual user settings.

# Background & Problem Statement

The client has an existing Claude deployment with a Microsoft 365 connector configured via Microsoft Entra ID. Access to the connector is restricted to a defined user group, and Outlook permissions have been removed tenant-wide to limit data exposure.

A requirement has emerged for one specific user to access Outlook through Claude without extending that access to others. The pre-built connector cannot accommodate this without one of the following compromises:

- Granting all users Outlook access (unacceptable — creates unapproved access risk)

- Relying on users to self-manage their tool settings (unacceptable — no central enforcement or audit)

A custom MCP server resolves this by placing access control logic server-side, where it can be centrally managed, audited, and scaled.

# Solution Overview

The proposed architecture replaces the pre-built Claude M365 connector with a custom-built MCP server hosted on the client's infrastructure (recommended: Azure App Service). The server acts as a controlled middleware layer between Claude and the Microsoft Graph API.

Architecture:

Claude (claude.ai) → Custom MCP Server (Azure) → Microsoft Graph API → M365 Data

How per-user scope control works:

- Each user authenticates through the custom MCP server using OAuth 2.0 (auth code flow)

- The server reads the user's assigned Entra App Role at authentication time

- Based on that role, the server requests only the Graph API scopes that user is permitted to use

- SharePoint-only users receive a token scoped to Sites.Read.All

- The Outlook-enabled user receives an additional token scoped to Mail.Read and related mail permissions

- No user can exceed their assigned permissions — enforcement is server-side

# Project Plan & Scope of Work

## Phase 1 — Discovery & Architecture

Define requirements, confirm infrastructure, and produce a detailed technical design before any build begins.

| Task / Deliverable | Description | Est. Hours | Rate / Cost |
| --- | --- | --- | --- |
| Requirements workshop | Confirm user groups, scope requirements, hosting environment, and Entra tenant access | 2 | [$ TBD] |
| Technical design document | Document architecture, Entra app registration design, OAuth flow, and role mapping schema | 4 | [$ TBD] |
| Infrastructure decision | Confirm hosting platform (Azure App Service recommended), runtime (C# .NET), and deployment model | 1 | [$ TBD] |

| Phase 1 Subtotal | 7 hrs | [$ TBD] |
| --- | --- | --- |

## Phase 2 — Entra ID Configuration

Register and configure a new Entra application with the appropriate Graph API scopes and App Role definitions.

| Task / Deliverable | Description | Est. Hours | Rate / Cost |
| --- | --- | --- | --- |
| Entra App Registration | Create new app registration separate from Anthropic's pre-built connector apps | 1 | [$ TBD] |
| Graph API scope configuration | Define and configure Sites.Read.All and Mail.Read (+ related) scopes on the registration | 1 | [$ TBD] |
| App Role definitions | Define SharePoint.Only and SharePoint.And.Outlook app roles within the registration | 1 | [$ TBD] |
| User/group role assignments | Assign all existing connector users to SharePoint.Only role; assign designated Outlook user to SharePoint.And.Outlook role | 1 | [$ TBD] |
| Admin consent | Grant tenant-wide admin consent for required Graph API permissions | 0.5 | [$ TBD] |

| Phase 2 Subtotal | 4.5 hrs | [$ TBD] |
| --- | --- | --- |

## Phase 3 — MCP Server Development

Build the custom MCP server implementing the MCP protocol, OAuth 2.0 auth code flow, and per-user scope logic.

| Task / Deliverable | Description | Est. Hours | Rate / Cost |
| --- | --- | --- | --- |
| Project scaffolding | Set up server project (C# .NET), MCP SDK integration, dependency management, and repo structure | 3 | [$ TBD] |
| OAuth 2.0 implementation | Implement auth code flow against Entra ID; handle token acquisition, refresh, and secure storage | 6 | [$ TBD] |
| App Role scope mapping | Logic to read authenticated user's Entra App Role and request appropriate Graph API scopes accordingly | 4 | [$ TBD] |
| MCP tool definitions | Implement MCP-compliant tool endpoints for SharePoint (file listing, search, read) and Outlook (mail read, search) | 6 | [$ TBD] |
| Graph API integration | Wire MCP tools to Microsoft Graph API calls; handle pagination, errors, and throttling | 4 | [$ TBD] |
| Logging & audit trail | Implement structured logging of all authentication events and tool invocations (user, scope, timestamp) | 2 | [$ TBD] |

| Phase 3 Subtotal | 25 hrs | [$ TBD] |
| --- | --- | --- |

## Phase 4 — Hosting & Deployment

Deploy the MCP server to Azure, configure security hardening, and connect Claude to the new endpoint.

| Task / Deliverable | Description | Est. Hours | Rate / Cost |
| --- | --- | --- | --- |
| Azure App Service setup | Provision App Service plan, configure runtime environment, environment variables, and managed identity | 2 | [$ TBD] |
| TLS & endpoint security | Configure HTTPS, custom domain (if required), and IP allowlisting to Claude.ai egress ranges | 2 | [$ TBD] |
| CI/CD pipeline (optional) | Set up basic deployment pipeline for future updates (Azure DevOps or GitHub Actions) | 3 | [$ TBD] |
| Claude connector configuration | Register custom MCP server URL in Claude Team/Enterprise admin settings; remove pre-built connector | 1 | [$ TBD] |

| Phase 4 Subtotal | 8 hrs | [$ TBD] |
| --- | --- | --- |

## Phase 5 — Testing & Validation

Verify that access controls are correctly enforced across all user scenarios before go-live.

| Task / Deliverable | Description | Est. Hours | Rate / Cost |
| --- | --- | --- | --- |
| SharePoint-only user testing | Confirm SharePoint tool access works; confirm Outlook tools are absent/blocked for standard users | 2 | [$ TBD] |
| Outlook-enabled user testing | Confirm designated user receives both SharePoint and Outlook tool access as expected | 1 | [$ TBD] |
| Negative / boundary testing | Attempt to escalate scopes or bypass role assignment; confirm server-side enforcement holds | 2 | [$ TBD] |
| Audit log review | Validate that all authentication events and tool calls are correctly captured in logs | 1 | [$ TBD] |
| Client UAT sign-off | Guided walkthrough with client stakeholders; document and resolve any outstanding issues | 2 | [$ TBD] |

| Phase 5 Subtotal | 8 hrs | [$ TBD] |
| --- | --- | --- |

## Phase 6 — Documentation & Handover

Deliver operational documentation and conduct a knowledge transfer session with the client's team.

| Task / Deliverable | Description | Est. Hours | Rate / Cost |
| --- | --- | --- | --- |
| Technical documentation | Architecture diagram, Entra configuration reference, server runbook, and log access guide | 3 | [$ TBD] |
| Admin guide | Step-by-step guide for adding/removing users, changing role assignments, and rotating credentials | 2 | [$ TBD] |
| Knowledge transfer session | Live walkthrough with client IT team covering architecture, day-to-day management, and escalation paths | 2 | [$ TBD] |

| Phase 6 Subtotal | 7 hrs | [$ TBD] |
| --- | --- | --- |

# Project Summary & Pricing

| Phase | Est. Hours | Cost |
| --- | --- | --- |
| Phase 1 — Discovery & Architecture | 7 | [$ TBD] |
| Phase 2 — Entra ID Configuration | 4.5 | [$ TBD] |
| Phase 3 — MCP Server Development | 25 | [$ TBD] |
| Phase 4 — Hosting & Deployment | 8 | [$ TBD] |
| Phase 5 — Testing & Validation | 8 | [$ TBD] |
| Phase 6 — Documentation & Handover | 7 | [$ TBD] |
| TOTAL | 59.5 hrs | [$ TBD] |

Notes:

- Hours above are estimates. Final pricing to be confirmed based on client's confirmed hosting environment and any additional scope items identified during Phase 1.

- CI/CD pipeline in Phase 4 is optional — hours can be removed if not required.

- Ongoing hosting costs (Azure App Service) are separate and billed directly by Microsoft.

- Ongoing support and maintenance retainer available upon request.

# Assumptions & Dependencies

- Client has an active Microsoft 365 tenant with Entra ID (Azure AD) and global admin access available for the engagement.

- Azure subscription is available for hosting the MCP server (App Service or equivalent).

- Client has an active Claude Team or Enterprise plan with admin access to connector settings.

- Existing pre-built M365 connector will be decommissioned upon successful go-live of the custom server.

- Client IT team will be available for the Phase 1 requirements workshop and Phase 5 UAT sessions.

- Any additional Graph API scopes beyond SharePoint and Outlook mail are out of scope and would require a change request.

# Indicative Timeline

| Phase | Indicative Duration |
| --- | --- |
| Phase 1 — Discovery & Architecture | Week 1 |
| Phase 2 — Entra ID Configuration | Week 1–2 |
| Phase 3 — MCP Server Development | Week 2–3 |
| Phase 4 — Hosting & Deployment | Week 3–4 |
| Phase 5 — Testing & Validation | Week 4 |
| Phase 6 — Documentation & Handover | Week 4–5 |
| Estimated total project duration | 4–5 weeks from kick-off |

# Acceptance

By signing below, the client confirms agreement with the scope, approach, and estimated fees outlined in this proposal.

| Client Authorised Signatory Name / Title / Date | Service Provider Name / Title / Date |
| --- | --- |